🚀 AI LeadOS — Full Project Roadmap & Team Guide

ProyoTech Internship 2026

For the team: This document is your single source of truth for how we are building AI LeadOS. It covers every sprint, who is active when, how to work with Git, and what "done" means for each deliverable.

📌 Project Overview

| Property | Value |
| --- | --- |
| Total Sprints | 8 |
| Completed | Sprint 1- 4 ✅ |
| Remaining | Sprints 5 – 8 |
| Team Size | 8 members |
| Stack | NestJS · Next.js 14 · PostgreSQL · Prisma · Google Gemini AI |
| Repo | github.com/proyotech/AI_LeadOS |
| Base Branch | main (always production-ready) |

👥 Team Structure & Roles

| Name | Team | Role |
| --- | --- | --- |
| Arpan | AI + Automation | Tech Lead · AI Engineer · Automation Engineer |
| Soumya | AI + Automation | AI Engineer · Automation Engineer |
| Dushyant | Backend | Backend Developer |
| Saransh | Backend | Backend Developer |
| Ujjwal | Backend | Backend Developer |
| Arav | Frontend | Frontend Developer |
| Harshwardhan | Frontend | Frontend Developer |

🔄 Sprint Rotation Strategy

To keep the codebase conflict-free, only one member per team is active in each sprint. The inactive member reviews PRs, studies the codebase, and prepares for their upcoming sprint.

| Sprint | Backend (rotates: D → S → U → D…) | Frontend (rotates: Arav → Harsh → …) | AI + Automation (rotates: Arpan → Soumya → …) |
| --- | --- | --- | --- |
| Sprint 1 ✅ | — (Arpan solo bootstrap) | — | Arpan |
| Sprint 2 🔵 | Dushyant | Arav | Arpan |
| Sprint 3 🟡 | Saransh | Harshwardhan | Soumya |
| Sprint 4 🟠 | Ujjwal | Arav | Arpan |
| Sprint 5 🔴 | Dushyant | Harshwardhan | Soumya |
| Sprint 6 🟣 | Saransh | Arav | Arpan |
| Sprint 7 🟢 | Ujjwal | Harshwardhan | Soumya |
| Sprint 8 🏁 | Dushyant | Arav | Arpan |

Inactive members: Review the active member's PR, read the new code, and use the sprint to prepare questions, set up your local dev environment, and study the relevant docs.

🌿 Git Workflow (Everyone Must Follow This)

main                          ← protected, never push directly
└── sprint-N/feature-name     ← your working branch

Branch Naming

sprint-2/leads-backend        ← backend feature
sprint-2/leads-ui             ← frontend feature
sprint-2/ai-auto-score        ← AI feature
fix/lead-score-bug            ← bug fix
docs/update-roadmap           ← documentation only

Commit Convention

feat: add lead CRUD endpoints
fix: correct null check in leads service
docs: update sprint 2 architecture
test: add unit tests for auth service
refactor: extract lead validation to guard

Pull Request Rules

- Branch from main, never from another feature branch

- PR title must follow commit convention (feat:, fix:, etc.)

- At least 1 reviewer must approve before merging (the inactive team member reviews)

- Copilot review is automatic — address all High/Medium comments before merging

- Delete your branch after merge

- PR description must include: what was built, how to test it, checklist

📅 Sprint-by-Sprint Plan

✅ Sprint 1 — Foundation & Setup

Status: Merged to main (Completed 19 June) Active: Arpan (solo bootstrap)

Sprint 1 was completed structured by Arpan to set up the foundation for everyone.

Arpan — Setup & Foundation

Task

NestJS backend scaffold + PostgreSQL Docker

Prisma schema — 11 models

Auth Module (register / login / me + JWT)

RolesGuard + RBAC

Next.js 14 frontend scaffold

Login / Register pages

Dashboard shell (sidebar + topbar)

AI Service Layer (Gemini wrapper + 4 prompts)

Workflow + Sequence + Event schemas

Automation Engine stub

🔵 Sprint 2 — Core CRM: Leads, Deals & Dashboard Data

Status: 🟡 Active
Goal: Real CRM data layer — leads & deals CRUD, live dashboard stats, AI auto-scoring.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Dushyant | sprint-2/backend |
| Frontend | Arav | sprint-2/frontend |
| AI + Automation | Arpan | sprint-2/ai-automation |

Dushyant — Backend (sprint-2/backend)

Task

LeadsModule — GET /leads, POST /leads, PATCH /leads/:id, DELETE /leads/:id

DealsModule — CRUD with stage transitions

Pagination, filtering & search on GET /leads

GET /dashboard/stats — total leads, deals, conversion rate

Input validation DTOs for all new endpoints

Swagger docs for all new endpoints

Arav — Frontend (sprint-2/frontend)

Task

Leads List page (/leads) — data table with search / filter / sort

Add Lead modal — form connected to POST /leads

Lead detail side panel — view / edit lead info

Dashboard home — connect stats cards to real GET /dashboard/stats

Reusable DataTable, Modal, Badge components

Design refinements — Tailwind colour tokens & typography

Arpan — AI + Automation (sprint-2/ai-automation)

Task

Trigger scoreLead() automatically on POST /leads creation

Store AI score + reasoning back to Lead.score in DB

Display AI score badge on leads list UI

Wire up InMemoryEventBus to fire lead.created event

🟡 Sprint 3 — Pipeline, Activity Feed & Task Management

Status: Upcoming
Goal: Kanban pipeline, per-lead activity timeline, task management.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Saransh | sprint-3/backend |
| Frontend | Harshwardhan | sprint-3/frontend |
| AI + Automation | Soumya | sprint-3/ai-automation |

Saransh — Backend

Task

TasksModule — CRUD for tasks with lead association

ActivitiesModule — log activity (call, email, note, WhatsApp)

Pipeline stage-change endpoint with activity auto-log

GET /leads/:id — full lead detail with deals, tasks, activities, AI insights

Harshwardhan — Frontend

Task

Pipeline page (/pipeline) — Kanban board with drag-and-drop deal cards

Deal card component — stage badge, amount, owner avatar

Activity timeline component — chronological feed per lead

Task management sidebar — add/complete tasks on lead detail

Lead detail page (/leads/:id) — full 360° view

Soumya — AI + Automation

Task

Wire InMemoryEventBus → lead.status_changed on pipeline stage change

Wire task.completed event when task is marked done

Auto-trigger scoreLead() on status change (re-score as lead progresses)

🟠 Sprint 4 — AI Intelligence Module & Outreach Sequences

Status: Upcoming
Goal: Real per-lead AI analysis (company audit), outreach sequence builder.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Ujjwal | sprint-4/backend |
| Frontend | Arav | sprint-4/frontend |
| AI + Automation | Arpan | sprint-4/ai-automation |

Ujjwal — Backend

Task

SequenceModule — CRUD for sequences and steps

Enroll lead endpoint — POST /sequences/:id/enroll/:leadId

AIInsightModule — POST /leads/:id/analyze endpoint

Store AI insights to AIInsight DB model

Arav — Frontend

Task

AI Intelligence page (/ai-intelligence) — company audit UI

AI insight cards — score, opportunities, risks, next action

Sequence builder UI — step editor with channel/delay/template fields

Sequence enrollment — select leads and enroll from the UI

Arpan — AI + Automation

Task

analyzeCompany() — wire to POST /leads/:id/analyze endpoint

generateOutreachSequence() — generate and persist 7-day plan per lead

Persist generated sequence steps to DB via SequenceModule

🔴 Sprint 5 — Automation Builder (Visual Workflow Editor)

Status: Upcoming
Goal: Drag-and-drop visual workflow builder with real DB-backed execution engine.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Dushyant | sprint-5/backend |
| Frontend | Harshwardhan | sprint-5/frontend |
| AI + Automation | Soumya | sprint-5/ai-automation |

Dushyant — Backend

Task

WorkflowModule — CRUD for workflows (persist definition to DB)

WorkflowExecutionModule — start, pause, stop, view logs

Schedule cron-triggered workflows (@nestjs/schedule)

Harshwardhan — Frontend

Task

Visual workflow canvas (/automation) — React Flow integration

Trigger node panel — 8 trigger types

Action node panel — 12 action types

AI Decision node — branching on AI score

Workflow run history panel

Soumya — AI + Automation

Task

Replace in-memory engine with DB-backed workflow executor

Integrate suggestWorkflows() to recommend automations to users

Per-node execution result tracking and logging

🟣 Sprint 6 — Communications Hub (Email, WhatsApp, LinkedIn)

Status: Upcoming
Goal: Outbound communication channels connected to the CRM.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Saransh | sprint-6/backend |
| Frontend | Arav | sprint-6/frontend |
| AI + Automation | Arpan | sprint-6/ai-automation |

Saransh — Backend

Task

Email integration (Resend / Nodemailer) — send template emails from sequences

WhatsApp integration (Meta Cloud API or Twilio)

CommunicationLog model — store every outbound/inbound message per lead

Deliverability tracking — open/click/bounce webhook handlers

Arav — Frontend

Task

Communications Hub page (/communications) — unified inbox

Conversation thread view per lead (WhatsApp-style)

Email composer with template variables

Arpan — AI + Automation

Task

AI-personalised message generation — use Gemini to write outreach copy

Auto-enroll leads in sequences based on communication triggers

Smart send-time optimisation prompt

🟢 Sprint 7 — Analytics, Reporting & Admin Panel

Status: Upcoming
Goal: Charts dashboard, team performance metrics, admin user management.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Ujjwal | sprint-7/backend |
| Frontend | Harshwardhan | sprint-7/frontend |
| AI + Automation | Soumya | sprint-7/ai-automation |

Ujjwal — Backend

Task

Analytics endpoints — conversion funnel, revenue pipeline, source breakdown

Lead velocity metrics (time from NEW → CONVERTED)

Team performance endpoint — activities per executive, deals won

Admin user management endpoints

Harshwardhan — Frontend

Task

Analytics page (/analytics) — Recharts / Chart.js

Conversion funnel chart + pipeline value by stage

Team leaderboard panel

Admin panel (/admin) — manage users, roles, settings

Soumya — AI + Automation

Task

AI weekly performance summary — Gemini-generated report

Predictive deal close probability using AI scoring history

Anomaly detection — flag leads with no activity in X days

🏁 Sprint 8 — Polish, Production Readiness & Launch

Status: Upcoming
Goal: Deployment, security hardening, final demo.

| Team | Active Member | Branch |
| --- | --- | --- |
| Backend | Dushyant | sprint-8/backend |
| Frontend | Arav | sprint-8/frontend |
| AI + Automation | Arpan | sprint-8/ai-automation |

Dushyant — Backend + DevOps

Task

docker-compose.prod.yml — production-ready multi-container setup

CI/CD pipeline (GitHub Actions) — lint, build, test on every PR

Environment secret management (Railway / Render / VPS)

Rate limiting, helmet, CORS hardening

Arav — Frontend

Task

Performance audit — Lighthouse score > 90

Mobile responsiveness pass on all pages

Loading skeletons, error boundaries, toast notifications

Arpan — AI + Automation + Final Docs

Task

Final AI prompt review — accuracy, latency, token cost

Full regression test: all AI + automation user flows

Final README.md production setup guide

Record demo video of the platform

Sprint 8 review presentation

🗓️ Sprint Timeline Overview

Sprint 1  ✅  Foundation & Setup                  19 June
Sprint 2  🔵  Core CRM — Leads, Deals, Dashboard  26 June
Sprint 3  🟡  Pipeline, Activities, Tasks          3 July
Sprint 4  🟠  AI Intelligence & Sequences          8 July
Sprint 5  🔴  Automation Builder (Visual)          11 July
Sprint 6  🟣  Communications Hub                  15 July
Sprint 7  🟢  Analytics & Admin                   18 July
Sprint 8  🏁  Polish, Deploy & Launch              22 July

📋 Definition of Done (Every Sprint)

Before any branch is merged to main:

- Feature fully implemented as described in this roadmap

- TypeScript compiles with no errors (npx tsc --noEmit)

- Swagger docs updated for all backend endpoints

- No hardcoded secrets or .env values in code

- Copilot High/Medium severity comments addressed

- PR description: what was built + how to test

- At least 1 peer review approval

- Branch deleted after merge

⚠️ Team Rules (Non-Negotiable)

- Never push directly to main — always open a PR

- Always git pull origin main before creating your branch

- One person per branch — never share a working branch

- Commit and push daily — don't sit on uncommitted work

- Read every merged PR description — know what changed

- Prisma schema is shared — coordinate with the active backend dev before touching it

- If you're stuck, speak up immediately — don't stay blocked silently

- Inactive sprint? Still review PRs and study the new code — stay sharp

🔗 Key Resources

| Resource | Link |
| --- | --- |
| GitHub Repo | github.com/proyotech/AI_LeadOS |
| Notion Board | (link shared by Arpan) |
| Swagger API Docs | http://localhost:3001/api/docs |
| Architecture Doc | docs/SPRINT_1_ARCHITECTURE.md |
| PR Template | docs/PR_Description_Sprint1.md |
| Sprint 2 Task Sheet | docs/SPRINT_2_TASKS.md |
| Env Template | backend/.env.example |

🚦 Quick Start for Every Member

# 1. Clone the repo (first time only)
git clone https://github.com/proyotech/AI_LeadOS.git
cd AI_LeadOS

# 2. Always start from latest main
git checkout main
git pull origin main

# 3. Create your sprint branch (use the name from your task sheet)
git checkout -b sprint-2/backend        # example

# 4. Backend setup
cd backend
npm install
cp .env.example .env
# Fill in: DATABASE_URL, JWT_SECRET, PGADMIN_DEFAULT_PASSWORD
docker-compose up -d
npx prisma migrate dev
npm run start:dev       # → http://localhost:3001/api/docs

# 5. Frontend setup (new terminal)
cd ../frontend
npm install
echo "NEXT_PUBLIC_API_URL=http://localhost:3001/api" > .env.local
npm run dev             # → http://localhost:3000

# 6. Commit and push your work
git add .
git commit -m "feat: your feature description"
git push origin sprint-2/backend

# 7. Open a Pull Request on GitHub → base: main